## Project Scheduling
Project Scheduling

This report shows a sample of project scheduling using a gantt chart.

Design

January 2007 / February 2007 / March 2007 / March 2007 / Requirements / Concept / Class design / Data structure / GUI design / Final check
	Task name					Start			End					Days

	Requirements					01.02.2007			08.02.2007
					7

	Concept					08.02.2007			15.02.2007
					7

	Class design					16.02.2007			28.02.2007
					12

	Data structure					01.03.2007			12.03.2007
					11

	GUI design					13.03.2007			17.03.2007
					4

	Final check					18.03.2007			20.03.2007
					2

	Statistics:
			Tasks sorted by their effort
0 / 2 / 5 / 8 / 10 / 12 / Class design / Data structure / Concept / Requirements / GUI design / Final check
					Duration of current phase:
					43

Programming

March 2007 / April 2007 / April 2007 / May 2007 / Coding Feature / Coding DB / Coding GUI / Unit Tests
	Task name					Start			End					Days

	Coding Feature					21.03.2007			10.04.2007
					20

	Coding DB					11.04.2007			24.04.2007
					13

	Coding GUI					25.04.2007			12.05.2007
					17

	Unit Tests					13.05.2007			17.05.2007
					4

	Statistics:
			Tasks sorted by their effort
0 / 2 / 5 / 8 / 10 / 12 / 15 / 18 / 20 / Coding Feature / Coding GUI / Coding DB / Unit Tests
					Duration of current phase:
					54

Test

May 2007 / May 2007 / June 2007 / June 2007 / Build Test Plans / Review / Execute Tests / Fixing Defects / Regress Test / Deliver Beta Build
	Task name					Start			End					Days

	Build Test Plans					18.05.2007			22.05.2007
					4

	Review					23.05.2007			25.05.2007
					2

	Execute Tests					26.05.2007			27.05.2007
					1

	Fixing Defects					28.05.2007			09.06.2007
					12

	Regress Test					10.06.2007			12.06.2007
					2

	Deliver Beta Build					13.06.2007			15.06.2007
					2

	Statistics:
			Tasks sorted by their effort
0 / 2 / 5 / 8 / 10 / 12 / Fixing Defects / Build Test Plans / Deliver Beta Build / Regress Test / Review / Execute Tests
					Duration of current phase:
					23

					Page 1

© 2005-2024, i-net software GmbH